## Project Flow
| Project Name | CHEFFY
| Start Date | 2021-06-01
| End Date | 2021-06-11
Sl.no | Tasks | Responsible | Start | End | Status
1 | Swagger Integration and Auditor aware Implimentation | Akash Konnur | 2021-06-01 | 2021-06-01 | Completed and Tested
2 | Backend for Authorization and Authentication | Akash Konnur, Akash Kumar and Sarthak | 2021-06-01 | 2021-06-03 | Completed and Tested
3 | Front end for Logging in and LoggingOut | Vikash Deep and Ankita | 2021-06-01 | 2021-06-03 | Completed and Tested
4 | Integration of Task 1 and 2 | Sarthak Nagpal | 2021-06-03 | 2021-06-03 | Completed and Tested
5 | Customer Registeration UI | Akash Kumar | 2021-06-04 | 2021-06-04 | Completed and Tested
6 | Chef Registeration UI | Vikash Deep and Ankita | 2021-06-04 | 2021-06-04 | Completed and Tested
7 | Customer Registeration Backend | Sarthak Nagpal | 2021-06-04 | 2021-06-04 | Completed and Tested
8 | Chef Registeration Backend | Akash Konnur | 2021-06-04 | 2021-06-04 | Completed and Tested
9 | Mid Stage Application testing and Integration and beginning of test driven approach | All Together | 2021-06-07 | 2021-06-07 | Completed and Tested
10 | Email Integration | Akash Kumar | 2021-06-07 | 2021-06-08 | Completed and Tested
11 | Stripe Payment Integration | Sarthak Nagpal | 2021-06-07 | 2021-06-08 | Completed and Tested
12 | Chef Booking Module | Akash Konnur | 2021-06-07 | 2021-06-08 | Completed and Tested
13 | Orders Page | Vikash Deep and Ankita | 2021-06-07 | 2021-06-08 | Completed and Tested
14 | Payment Page | Sarthak Nagpal | 2021-06-08 | 2021-06-09 | Completed and Tested
15 | Order Summary page | Vikash Deep, Sarthak Nagpal | 2021-06-08 | 2021-06-09 | Completed and Tested
16 | Order Processing Module | AKash Kumar, Akash Konnur | 2021-06-08 | 2021-06-09 | Completed and Tested
17 | Profile Page | Akash Kumar | 2021-06-09 | 2021-06-10 | Completed and Tested
18 | My Orders/ My Allocation | Sarthak Nagpal, Vikash Deep | 2021-06-10 | 2021-06-10 | Completed and Tested
19 | Backend for Allocation, Profile and My Orders | Akash Konnur | 2021-06-10 | 2021-06-10 | Completed and Tested
20 | Module for booking Cooks, change Password and Forgot password | Akash Konnur | 2021-06-10 | 2021-06-10 | Completed and Tested
21 | End - End Integration and Validations | All Together | 2021-06-10 | 2021-06-10 | Completed and Tested
22 | Git Pipelining and CI/CD Integration | All Together with Devops Team | 2021-06-11 | 2021-06-11 | Completed and Tested
Sl.no | Possible Enhancements
1 | UI for Change password
2 | UI for Forgot password
3 | Caching for Performance Enhancement
4 | Running Discount offers
5 | OTP based login
6 | re-initiating payment on failed orders
7 | Chef accepting or rejecting orders

## Issues
Sl.no | Issue | Responsible Person | Reported-by | Status
1 | All post requests rejected irrespective of authorization | Akash Konnur | Sarthak Nagpal | Resolved
2 | Detached object, Hibernate exception | Sarthak Nagpal | Akash Konnur | Resolved
3 | Data integrity exception not handled correctly | Akash Konnur | Sarthak Nagpal | Resolved
4 | Book Chef Page not responsive | Akash Kumar | Sarthak Nagpal | Resolved
5 | Password encoding not used meticulously | Sarthak Nagpal | Akash Konnur | Resolved
6 | Loader not showing Corretly | Sarthak Nagpal | Sarthak Nagpal | Resolved
7 | Login module returning Primary User, but need to return Id of Chef or Customer based on request | Akash Konnur | Sarthak Nagpal | Resolved
8 | Chef tier was always posting 0 irrespective of selection | Akash Kumar | Vikash Deep | Resolved
9 | Order summary page not responsive | Sarthak Nagpal | Sarthak Nagpal | Resolved
10 | Payment processing page non responsive | Sarthak Nagpal | Sarthak Nagpal | Resolved

## Features
Sno. | Feature | Approach | Backend table
1 | Self register user/cook |  | Users,role
2 | Reset password | email/otp
3 | Login & authentication | users or chef | Users,role,chef details
4.1 | Users screen |  | user details
4.2 | Chef screen |  | chef details
5 | Junit5 - testing
6 | Business rules

## Business Rules
Rules |  | gettTire(){
3> yrs | 1 | }
2> <3 | 2
<1 | 3

## Data Models
User | Customer | Chef | Role | UserRole | Address | ChefDetail | S3 Images | Audit Fields
Id(Auto) | User | User | Id | Id | Id | Id | returns url | CreatedBy
Name | other customer sepcif details | other chef related fields | Name | UserId | Address Line 1 | Experience |  | CreatedDate
Password |  |  |  | RoleId | Address Line2 | TotalOrders |  | UpdatedBy
phoneNumber |  |  |  |  | City | UserId |  | UpdatedDate
Email |  |  |  |  | State | Hotel
Photo (string) |  |  |  |  | Pin
Lattitude
Longitude
Order | Payment | Transaction
Id | Id | Id
Date | PaymentDate | Order
ConsumerId references Customer | PaymentStatus | Payment
ChefId referecnces Cheff | Mode | Amount
List<PaymentId>
| Id | 1 | 2 |  |  | 5500 |  | Customers | Chef
| Date | 31 | 30 |  |  | Success |  | Akash(1) | Kumar(4)
| ConsumerId | 1 | 3 |  |  |  |  | Ankita(2) | Vikash(5)
| ChefId | 5 | 4 |  |  |  |  | Sarthak(3)
| PaymentId | 76 | 77

## End Points
sl no | Base Table | End point
1 | User | Register(post) (security bypass)
2 | User | Reset Password

## Doubts
1 | For cuisine and occasions, is admin section needed?
2 | Google maps not free?
3 | Get all users with role Chef
4 | What happens chef rejects order
5 | React should user TS ?
6 | photo is optional

## Sheet1
login -> book -> tier 1 -> slot -> Subscription -> ... chef accepts... -> 5000 -> you have to pay 2000 -> continue -> PAY -> save in database
Bookings
Chef 1.1 | 1 month 8.30-9.30 morning | Id | chefID | Date | From | To
Chef 2.1
Chef 2.2
Chef2.3
Chef 3.1
Chef3.2
Chef3.3

## Sheet2
next 3 months we will store slots | order_request | status
pending
SLOT | Chef_Slot
Id | SlotId | 1 | 2
Beginning time | Chef_id | 1 | 1
ChefA (tire1) | CustomerA |  |  |  | 5
customer A books chefA for 1 month daily 9-10
| customerB | 9->10 june 5
Slot |  | Customer_slot
1 |  | Chef_A | booked | 1
2009-06-03 |  | Chef_A | booked | 2
3 june 9.30
3.june 10

## Sheet3
example
Slot_id | Date | Time | Slot_allocation |  |  | Customer |  | Tier1
1 | 2021-06-03 | 9 | SlotId | Chef_Id | Is_booked | 1 | Customer A | id | NAme
2 | 2021-06-03 | 9.3 | 1 | 1 | TRUE | 2 | Customer B | 1 | Chef A | N-A
3 | 2021-06-03 | 10 | 2 | 1 | TRUE |  |  | 2 | Chef B
4 | 2021-06-03 | 10.3 | 49 | 1 | TRUE |  |  | 3 | Cheff C
5 | 2021-06-03 | 11 | 50 | 1 | TRUE
6 | 2021-06-03 | 11.3 | 49 | 2 | TRUE
7 | 2021-06-03 |  | 50 | 2 | TRUE
8 | 2021-06-03
9 | 2021-06-03
10 | 2021-06-03
11 | 2021-06-03
12 | 2021-06-03
49 | 2021-06-04 | 9
50 | 2021-06-04 | 9.3
150 | 7 th june | 9
9.3

## Research
1 | Adding and retrieving images in AWS S3
2 | Stripe payment gateway / mock database

## Resources
Order | confirmed_orders | Payment
1 | order_id | confirmed_order_id
2 | chef_id | amount
3 | Customer_id | payType
4 | transactionId | transactionId
customer_id
status :Allocated
Amount